Minutes of Management Meeting Held on September 28, 2026

Attendance

Mr. Henry Ezike

Mr. Desmond

Ms. Chiamaka Nwantwo

Ms. Vivian Iyaha

Ms. Princess Obaseki

Mr. Lanre Adebayo

Mr. Harrison Obayi

Mr. Emmanuel Udo

Mr. Kenneth Onyemachi

Start Time: 10:08 AM

End Time: 2:41 PM

Opening Prayer: Led by Ms. Chiamaka Nwankwo

Amendments: There were no amendments to the opening records.

Adoption: The motion for adoption was moved by Ms. Princess and seconded by Ms. Chiamaka Nwankwo.

MATTERS ARISING

Visa Certification: Ms. Princess reported that the audit report was sent, and the visa team has requested a sample.

UBA SL Visa Platinum Card: Mr. Kenneth reported that UBA Nigeria requested that we share previous discussions regarding personalization, which has been done. We are currently awaiting their feedback.

UBA Liberia: IT noted that test data for UBA Liberia will be sent to the client.

Glo One Pin Applet: Mr. Kenneth reported that we are still expecting chip modules for production to commence.

Wema Afrigo: Mr. Kenneth reported there are no updates regarding the missing key.

Lotus Bank: Mr. Kenneth reported following the mail trail, indicating that most shortfalls originated from the bank due to modifications they made without communication, noting that each notification requires a new artwork. Ms. Princess added that the client complained our team doesn’t respond to mails. Also, she suggested substituting another company due to ECP delays.

Daily Production Plan: MD instructed that the daily production plan should not be limited to perso and PMC. He mandated that the daily production plan must be signed by all production before the commencement of production.

CIM: Mr. Kenneth reported that the meeting is scheduled to hold Wednesday September 30, 2026.

Airtel PUK: Mr. Kenneth reported that Ho & Bro suggested that card readers should be dispatched to the Airtel outlet, or all SIM cards should be retrieved for in-house rectification. Though, both are not feasible. Mr. Kenneth suggested personalizing about 500 cards for a "welcome back" initiative.

Opay Duplicate Cards: Ms. Chiamaka Nwankwo reported that the cards have not yet been received from Opay.

Infrastructure & Building Project: Mr. Lanre reported that the building project is still ongoing and casting will begin before the end of the week. Additionally, two containers are currently being negotiated for purchase so that machinery can be transferred to the new ones.

Dress code update: Differentiate the coveralls of the head unit from regular team members. Ensure correct Personal Protective Equipment (PPE) is utilized.

Action Points:

- Admin: Follow up on the Starlink business line and provide an update.

- CISO: Submit weekly security report.

- Maintenance: Provide a comprehensive list of spare parts required for CTP maintenance.

- Maintenance: Submit a report on the CTP installation and details of the advance payment made.

- Admin: Submit a complete record of all air-conditioning units (ACs), including both functional and non-functional units identified during the audit.

- Maintenance: Follow up on the relocation plans for the moved chiller and provide an update.

- Production: Ensure all production units maintain and update a daily production plan.

- Maintenance: Arrange for the rental of a battery to support forklift operations.

- Business & Accounts: Process compassionate leave requests and related leave payments accordingly.

- Accounts: Ensure payment of Glo and other applicable VAT obligations is completed within the week.

- IAC: Coordinate and complete the replacement of the fire alarm panel.

- Business Team: Conduct business visits to Lotus Bank and Polaris Bank and provide feedback following the visits.

DEPARTMENTAL REPORTS

Adjournment

The meeting was adjourned following a motion moved by Mr. Harrison and seconded by Mr. Kenneth at 2:41 PM.